## Implementation Checklist
HR Software Implementation Checklist - Bangladesh
Work through this before, during and after go-live. Free resource from Tipsoi.
1. Objectives & scope (before you shortlist a vendor)
☐ | Written business objective for the rollout (not 'buy HR software') with named executive sponsor
☐ | Define what 'adoption' means in numbers (e.g. % of employees using self-service monthly)
☐ | Map and document every current HR process AS-IS, including informal/manual rules
☐ | List the custom rules only senior staff know (payment calculations, shift exceptions, allowances)
☐ | Budget includes hidden costs: data cleansing, customisation, integration, training, post-launch support (AMS)
☐ | Timeline includes buffer for unforeseen delays
2. Data readiness (the #1 source of go-live mistrust)
☐ | Full audit of employee master data: NID, joining date, grade, salary structure, allowances
☐ | Cleanse duplicates, incomplete records and outdated entries BEFORE migration
☐ | Verify employment history and leave balances against source records
☐ | Agree a data owner for each field
☐ | Run at least one FULL parallel payroll cycle (old system + new system) and reconcile to zero
3. Bangladesh Labour Act 2006 compliance (configure, don't assume)
☐ | Overtime configured at twice the ordinary rate of basic wage (Section 108)
☐ | Casual leave: 10 days per calendar year, full wages, non-accumulable (Section 115)
☐ | Earned leave accrual: 1 day per 18 days worked for factory/shop/commercial workers (Section 117)
☐ | Festival holidays configured to your establishment's declared calendar
☐ | Legally mandated reporting formats can be generated from the system
☐ | Compliance audit done during testing - not after go-live
☐ | Do not accept a foreign vendor's default settings as compliant
4. Infrastructure reality check (load-shedding & connectivity)
☐ | Attendance and task logging keep working offline, then auto-sync when the link returns
☐ | Devices have battery backup; UPS budgeted for local network hardware
☐ | Test the system on a real site outside Dhaka before rollout
☐ | Mobile access tested on the handsets and data speeds your staff actually use
☐ | Documented fallback for a multi-hour outage on a payroll cut-off day
5. People & change management
☐ | Change champions named in every department/site
☐ | Communicate the 'what's in it for me' to employees, not just company benefits
☐ | Role-based training (HR admin vs manager vs employee self-service) - not one generic session
☐ | Training materials in the language your workforce uses
☐ | Hypercare support desk staffed for the first 30-40 days after go-live
☐ | Adoption measured monthly against the target you defined in section 1
6. Vendor & contract
☐ | Vendor track record checked with reference customers of similar size and industry
☐ | Confirm local support presence and escalation path
☐ | Written SLA for support response, monitoring and system updates AFTER go-live
☐ | Application Management Services (AMS) scope agreed and priced
☐ | Data export/exit clause: you can get your data out in a usable format
☐ | Scalability and security reviewed against your 3-5 year headcount plan
Made by Tipsoi · tipsoi.pro